## Submittal Parts List
DOUBLE RL RANCH - EAST CABINS IRRIGATION MAINLINE
SUBMITTAL PARTS LIST — Items Requiring New Submittals
Project #: 252128.ENV ¦ Engineer: JVA, Inc. ¦ Date: March 2026
Item # | Description | Size(s) | Qty | Source | Notes
1. HDPE PIPE
1 | DR11 IPS HDPE Pipe | 4" | 400 ft | Materials List | Mainline irrigation, 40' or 50' pieces
2 | DR11 IPS HDPE Pipe | 3" | 2,520 ft | Materials List | Mainline irrigation, 40' or 50' pieces
3 | DR11 IPS HDPE Pipe | 2" | 520 ft | Materials List | Mainline irrigation
4 | SDR11 IPS OD HDPE Pipe | 6" | 60 ft | Takeoff - Vault | Suction line + fire suppression
5 | SDR11 IPS OD HDPE Pipe | 4" | 20 ft | Takeoff - Vault | Filter to irrigation
6 | SDR11 IPS OD HDPE Pipe | 2" | 120 ft | Takeoff - Vault | Backwash, sump, suction
7 | SDR11 IPS OD HDPE Pipe | 3/4" | 20 ft | Takeoff - Vault | Backwash line
8 | DR11 IPS HDPE Duct (Orange) | 1.25" | 4,000 ft reel | Materials List | Low voltage signal wire duct
2. HDPE FITTINGS (Butt Fusion / Electrofusion)
9 | DR11 IPS HDPE 45° Elbow | 4" | 4 | Materials List
10 | DR11 IPS HDPE 22.5° Elbow | 4" | 2 | Materials List
11 | DR11 IPS HDPE 45° Elbow | 3" | 4 | Materials List
12 | DR11 IPS HDPE 22.5° Elbow | 3" | 4 | Materials List
13 | DR11 IPS HDPE 45° Elbow | 2" | 2 | Materials List
14 | DR11 IPS HDPE 22.5° Elbow | 2" | 2 | Materials List
15 | DR11 IPS HDPE Tee | 4"x3" | 2 | Materials List
16 | DR11 IPS HDPE Tee | 4"x2" | 3 | Materials List
17 | DR11 IPS HDPE Tee | 3"x3" | 6 | Materials List
18 | DR11 IPS HDPE Tee | 3"x2" | 2 | Materials List
19 | SDR11 IPS OD HDPE 90° Bend | 2" | 11 | Takeoff - Vault | Multiple systems
20 | SDR11 IPS OD HDPE 90° Bend | 3/4" | 1 | Takeoff - Vault
21 | SDR11 IPS OD HDPE Tee | 2" | 2 | Takeoff - Vault | Filter backwash
22 | SDR11 IPS OD HDPE Tee | 2"x3/4" | 1 | Takeoff - Vault | Hydropneumatic tank
23 | SDR11 IPS OD HDPE Reducer | 2"x3/4" | 2 | Takeoff - Vault
24 | SDR11 IPS OD Wall Anchor | 6", 4", 2" | 4 | Takeoff - Vault | Various systems
3. HDPE FLANGE ADAPTERS, BACKING RINGS & TRANSITION FITTINGS
25 | DR11 IPS HDPE Flange Adapter w/ Backing Ring | 3" | 6 | Materials List | Mainline, incl bolt kits
26 | DR11 IPS HDPE Flange Adapter w/ Backing Ring | 2" | 4 | Materials List | Mainline, incl bolt kits
27 | SDR11 IPS OD HDPE Flange Adapter | 6" | 5 | Takeoff - Vault | Incl backing rings
28 | SDR11 IPS OD HDPE Flange Adapter | 4" | 1 | Takeoff - Vault | Filter to irrigation
29 | SDR11 IPS OD HDPE Flange Adapter | 2" | 4 | Takeoff - Vault | Hydropneumatic tank
30 | SDR11 IPS OD HDPE MJ Adapter | 6" | 2 | Takeoff - Vault | Suction line
31 | SDR11 IPS OD HDPE MIPT Transition Adapter | 2" | 11 | Takeoff - Vault | Multiple systems
32 | SDR11 IPS OD HDPE FIPT Transition Adapter | 2", 3/4" | 2 | Takeoff - Vault
33 | SDR11 IPS OD HDPE MIPT Transition Adapter | 3/4" | 2 | Takeoff - Vault
34 | Mega Flange Adapter | 6", 4" | 11 | Takeoff - Vault | Various sizes across systems
4. DUCTILE IRON FLANGED FITTINGS
35 | DI Flanged Tee | 6"x4" | 2 | Takeoff - Vault | Suction line
36 | DI Flanged Tee | 4" | 3 | Takeoff - Vault | Discharge + fire suppression
37 | DI Flanged Tee | 4"x2" | 1 | Takeoff - Vault | Filter to irrigation
38 | DI Flanged 90° Bend | 4" | 3 | Takeoff - Vault | Discharge + fire suppression
39 | DI Flanged Reducer | 6"x4" | 1 | Takeoff - Vault | Fire suppression
40 | DI Flanged Reducer | 4"x3" | 3 | Takeoff - Vault | Suction + discharge
41 | DI Tapped Blind Flange | 6"x2" | 1 | Takeoff - Vault | Suction line
42 | DI Tapped Blind Flange | 4"x2" | 1 | Takeoff - Vault | Backwash
43 | DI Flange x PE Spool (various lengths) | 6", 4" | 10 | Takeoff - Vault | 1'-0" to 3'-6" lengths
5. FLANGE BOLT, NUT & GASKET KITS
44 | DI Flange Bolt, Nut & Gasket Kit | 6" | 3 | Takeoff - Vault
45 | DI Flange Bolt, Nut & Gasket Kit | 4" | 30 | Takeoff - Vault | Across all systems
46 | DI Flange Bolt, Nut & Gasket Kit | 3" | 4 | Takeoff - Vault
47 | DI Flange Bolt, Nut & Gasket Kit | 2" | 2 | Takeoff - Vault | Hydropneumatic tank
48 | HDPE Flange Bolt, Nut & Gasket Kit | 6", 4", 2" | 8 | Takeoff - Vault
49 | HDPE MJ Bolt, Nut & Gland Kit | 6", 2" | 4 | Takeoff - Vault
6. VALVES (Excluding Butterfly, Check, & Air Release)
50 | Resilient Wedge Epoxy Coated Gate Valve w/ HDPE Adapters | 3" | 5 | Materials List | DR11 IPS integrated adapters
51 | Resilient Wedge Epoxy Coated Gate Valve w/ HDPE Adapters | 2" | 3 | Materials List | DR11 IPS integrated adapters
52 | MJ Plug Valve | 6" | 1 | Takeoff - Vault | Suction line
53 | Flanged Plug Valve | 4" | 2 | Takeoff - Vault | Suction line
54 | Brass Ball Valve | 2" | 3 | Takeoff - Vault | Suction + backwash
55 | Brass Ball Valve | 3/4" | 7 | Takeoff - Vault | Multiple systems
56 | Flanged Pressure Reducing & Sustaining Valve (Solenoid Actuated) | 4" | 1 | Takeoff/Dwgs P2.0 | Fire suppression interconnect
57 | Pressure Reducing Valve | 2" | 1 | Takeoff - Vault | Intake screen backwash
58 | Pressure Reducing Valve | 1" | 1 | Dwgs P2.0/P2.1 | Intake screen backwash (per plan)
7. VALVE BOXES
59 | Cast Iron Valve Box w/ Lid (24"-30" bury) |  | 8 | Materials List | Mainline irrigation
60 | 546A Valve Box |  | 1 | Takeoff - Vault | Suction line plug valve
8. SERVICE SADDLES
61 | Saddle | 6"x3/4" | 1 | Takeoff - Vault
62 | Saddle | 4"x3/4" | 6 | Takeoff - Vault | Multiple systems
63 | Electrofusion Tap Saddle | 6"x4" | 1 | Dwg C2.0 | Civil site plan callout
9. BRASS FITTINGS
64 | Brass Nipple | 3/4"x2" | 7 | Takeoff - Vault
65 | Brass Nipple | 2"x4" | 2 | Takeoff - Vault
66 | Brass Tee | 3/4" | 1 | Takeoff - Vault
67 | Brass Street 90° Bend | 3/4" | 1 | Takeoff - Vault
68 | Brass Hex Bushing | 3/4"x1/4" | 6 | Takeoff - Vault | For pressure gauges
69 | Brass Swing Check Valve | 2" | 2 | Takeoff - Vault | Filter backwash
10. MAJOR EQUIPMENT
70 | Irrigation Pump — Goulds 46SV10GM4F60 |  | 2 | Dwg G1.0 | 200 GPM, 288 FT TDH, 25 HP, VFD
71 | Sump Pump — Zoeller Model 53 |  | 1 | Dwg G1.0 | 20 GPM, 19 FT TDH, 0.3 HP, Direct
72 | Hydropneumatic Tank |  | 1 | Takeoff/Dwgs | Per P&ID and vault plan
73 | Screen Filter |  | 1 | Dwgs P2.0/P2.1 | Per vault plan
74 | Flanged Flow Meter | 4" | 1 | Takeoff - Vault | Discharge line
75 | Intake Screen |  | 1 | Dwg C2.0/CD1.0 | Removable SS pipe anchors, precast box
11. TRACER WIRE & ACCESSORIES
76 | Blue Tracer Wire |  | 4,000 ft | Materials List
77 | Silicon Tube & Wire Nut Splice Kit |  | 20 | Materials List
EXCLUDED — Contractor Using Existing Vendor Submittals
— | Air Release Valves (AIRVAC Combo Valves) |  |  | EXCLUDED | Per 016-1087e DRLR submittal
— | Butterfly Valves (Wafer type) |  |  | EXCLUDED | Per 017-1087 DRLR submittal
— | Check Valves (Flanged) |  |  | EXCLUDED | Per 018-1087e DRLR submittal
— | Pressure Gauge Material |  |  | EXCLUDED | Per 026-1087e DRLR submittal